CIS 2987 — Capstone Final Report

AI-Powered Storytelling Tool for Nonprofits

| Student | Thomas Brett |
| --- | --- |
| Course | CIS 2987 — CIS Capstone |
| Report Date | April 26, 2026 |
| PM Tool | ClickUp |
| Stakeholder | Carlos Morales — Viva Technology LLC |

# 1. Project Summary

This capstone project produced a web-based, AI-powered storytelling tool designed to help nonprofit staff turn program experiences into publication-ready narrative drafts. The tool guides a staff member through a structured five-question interview, extracts a structured story summary, and automatically generates a polished narrative tailored to a selected goal and audience combination.

The application uses a deliberate two-model pipeline. A locally hosted Ollama instance running llama3.1:8b conducts the interview step at temperature 0.2 with a 16,384-token context window. Once all five story elements are collected and the model outputs a valid JSON object, that summary is passed to the Claude API (claude-sonnet-4-6, temperature 0.3, 2,048 max tokens), which generates the finished narrative according to goal-specific tone, length, and audience writing instructions.

The tool was developed over six weeks against a brief provided by stakeholder Carlos Morales of Viva Technology LLC, who supplied the content framework including six content goals, seven audience profiles, writing configs, and test stories. The finished application runs in Docker, is exposed for stakeholder access via ngrok with password-based authentication and was validated end-to-end against all six story starters Carlos provided.

# 2. Original Project Timeline

The project was scoped as a six-week build (Weeks 10–15 of the semester), with each week targeting a distinct layer of the application.

Week 1 — Foundation (Target: March 23, 2026)

Install Ollama, scaffold the Flask app using the app factory pattern with blueprints, and build goal and audience selection screens backed by Python config objects.

Week 2 — The Interview System (Target: March 29, 2026)

Build the multi-turn Ollama conversation loop, implement the five-question story extraction sequence via system prompt, establish server-side session state management, and produce structured JSON output at interview completion.

Week 3 — Refining The Interview System (Target: April 5–10, 2026)

Test the extraction pipeline against all six stakeholder story starters, fix edge cases (vague answers, one-word responses, off-topic inputs), validate consistent JSON output, and log extraction completion rates across all test runs.

Week 4 — Draft Generation (Claude API) (Target: April 13–17, 2026)

Integrate the Anthropic Claude API, build the prompt template that injects goal config, audience config, and the Step 3 JSON, and validate that goal-specific outputs are meaningfully distinct — specifically that donor appeal narratives close with a donation ask and volunteer recruitment narratives close with a volunteer invitation.

Week 5 — Quality Check + Output (Target: April 20–24, 2026)

Connect the full pipeline end-to-end, build the clean output screen with copy-to-clipboard, add the Flesch readability scorer, and add the hybrid PII detection scanner.

Week 6 — Final Report & Documentation (Target: April 26, 2026)

Write the capstone final report, produce the video walkthrough, and deliver final project documentation.

# 3. Completed Tasks — Full Log

All planned tasks were completed. The table below lists every task with its planned and actual completion date, estimated and actual hours, and variance. Color bands correspond to project weeks.

| Task | Planned Due | Completed | Est. | Actual | Variance |
| --- | --- | --- | --- | --- | --- |
| Week 1 |  |  |  |  |  |
| Install Ollama and pull the LLaMA 3 model | 03/23/2026 | 03/23/2026 | 0:30 | 0:30 | On target |
| Build a basic Flask web app skeleton | 03/23/2026 | 03/23/2026 | 0:45 | 0:45 | On target |
| Build Step 1 screen — goal selection dropdown | 03/23/2026 | 03/23/2026 | 0:45 | 0:45 | On target |
| Build Step 2 screen — audience selection dropdown | 03/23/2026 | 03/23/2026 | 0:45 | 0:45 | On target |
| Store goal/audience as full config objects | 03/23/2026 | 03/23/2026 | — | — | On target |
| Week 2 |  |  |  |  |  |
| Build the multi-turn conversation loop — AI remembers previous answers in the session | 03/29/2026 | 03/28/2026 | 2:00 | 2:30 | +0:30 |
| Implement the fixed 5-question extraction sequence using system prompt | 03/29/2026 | 03/28/2026 | 2:00 | 3:00 | +1:00 |
| Session state management working end-to-end | 03/29/2026 | 03/28/2026 | 1:00 | 1:00 | On target |
| Output a structured JSON object with the 5 story elements at the end of the interview | 03/29/2026 | 03/29/2026 | 1:30 | 2:00 | +0:30 |
| Week 3 |  |  |  |  |  |
| Test the extraction loop against all 6 story starters Carlos provided | 04/07/2026 | 04/08/2026 | 4:00 | 4:30 | +0:30 |
| Fix edge cases — vague answers, very short answers, off-topic responses | 04/08/2026 | 04/09/2026 | 3:00 | 3:30 | +0:30 |
| Confirm JSON output is consistently structured across all test runs | 04/09/2026 | 04/09/2026 | 2:30 | 2:30 | On target |
| Log the extraction completion rate across test stories | 04/10/2026 | 04/10/2026 | 1:30 | 1:30 | On target |
| Week 4 |  |  |  |  |  |
| Connect to Claude's API using the Anthropic API key | 04/14/2026 | 04/14/2026 | 4:00 | 4:00 | On target |
| Pass the Step 3 JSON + goal config + audience config into the Claude prompt template | 04/15/2026 | 04/15/2026 | 10:00 | 10:00 | On target |
| Handle the Claude API response and display the draft in the UI | 04/16/2026 | 04/16/2026 | 4:00 | 4:00 | On target |
| Confirm tone and length matches goal and audience config; verify Goal 5 produces donation ask, Goal 6 volunteer invitation | 04/17/2026 | 04/17/2026 | 7:00 | 7:00 | On target |
| Week 5 |  |  |  |  |  |
| Connect Steps 5 and 6 into the full pipeline | 04/21/2026 | 04/20/2026 | 6:00 | 6:00 | On target |
| Build the clean output screen — copy-paste ready narrative | 04/22/2026 | 04/21/2026 | 4:00 | 4:00 | On target |
| Build the Flesch readability score on the final draft | 04/23/2026 | 04/22/2026 | 2:00 | 2:00 | On target |
| Build PII detection — flag names, locations, and identifying details in the draft | 04/24/2026 | 04/23/2026 | 3:00 | 3:00 | On target |
| Week 6 |  |  |  |  |  |
| Final documentation, capstone report, and video walkthrough | 04/26/2026 | 04/26/2026 | 8:00 | 8:00 | On target |

# 4. Total Hours

PM / Reporting time (0:30 per week) covers updating ClickUp tasks, logging time, and preparing weekly progress reports, per capstone requirements.

| Week | Development | PM / Reporting | Week Total | Cumulative |
| --- | --- | --- | --- | --- |
| Week 1 — Foundation | 2:45 | 0:30 | 3:15 | 3:15 |
| Week 2 — The Interview System | 8:30 | 0:30 | 9:00 | 12:15 |
| Week 3 — Refining The Interview System | 11:30 | 0:30 | 12:00 | 25:15 |
| Week 4 — Draft Generation (Claude API) | 25:00 | 0:30 | 25:30 | 50:45 |
| Week 5 — Quality Check + Output | 15:00 | 0:30 | 15:30 | 66:15 |
| Week 6 — Final Report & Documentation | 7:30 | 0:30 | 8:00 | 74:15 |
| PROJECT TOTAL |  | 3:00 | 74:15 | 74:15 |

# 5. Tasks Not Completed

None. All tasks from the original six-week project plan were completed within the timeline. No features were cut or deferred.

# 6. Screenshots

Ollama Test – Week 1

Flask App – Week 1

Goals & Audiences Dropdowns – Week 1

Chat Screen – Week 2

Conversation Summary (note the issue with json coming in with the model’s question) – Week 2

Debug showing model context and token usage – Week 2

Flask Session Management – Week 2

Properly formatted JSON output – Week 2

Tested story extraction loop – Week 3

Iterate on system prompt – Week 3

Consistent JSON structure – Week 3

Claude API integration (blurred api key) – Week 4

Code excerpt showing how Claude is integrated – Week 4

Generated narrative from Claude API – Week 4

Flesch readability score integration – Week 5

PII detection and flagging – Week 5

PII Detection and flagging shown working alongside readability score -  Week 5

# 7. Final Documentation

The primary deliverable is the working application itself, accessible via the ngrok static domain with password authentication. The tool was validated end-to-end against all six story starters provided by the stakeholder and is demo-ready.

## Application Architecture

The application is built with Flask (Python 3) and runs inside Docker Compose. The entry point is run.py, which calls create_app() from the app factory in app/__init__.py. Routes are organized as a single Blueprint in app/routes.py.

Key components:

- Interview engine: Ollama API at http://localhost:11434, model llama3.1:8b, temperature 0.2, context window 16,384 tokens. The system prompt is loaded from config/system_prompt.txt at startup and injected as the first message in the messages array on every request so all model configurations receive it consistently.

- Narrative generation: Anthropic Python SDK (anthropic>=0.40), model claude-sonnet-4-6, temperature 0.3, max_tokens 2,048. The user prompt is assembled by build_narrative_prompt() in routes.py, which substitutes goal label, audience label, all five story fields, raw quotes, and the goal's tone/length/priority and the audience's reading level and values into a template loaded from config/claude_user_prompt.txt.

- Interview completion detection: after each Ollama response, the Flask layer checks whether the response text starts with '{' and ends with '}'. If so, it attempts json.loads(). On success, the extraction is saved as a JSON file to the interviews/ directory and the Claude API call fires automatically — no manual trigger required.

- Application-layer guardrails: one-word responses and known prompt injection phrases ('forget your system prompt', 'forget your instructions', 'your new instructions') are intercepted in routes.py before reaching the Ollama model. The last assistant message is returned instead, keeping the interview on track.

- Readability scorer: app/readability.py wraps textstat's flesch_reading_ease() and maps the raw score to one of seven grade bands (4th-5th grade at 90+ down to college graduate below 30). It parses the audience's target grade range from the config string and returns one of three match states — too_simple, too_complex, or matches — with a plain-language summary.

- PII scanner: app/pii.py uses a hybrid approach. Presidio's AnalyzerEngine (spaCy NER) detects names, locations, organizations, phone numbers, and email addresses. Six additional custom regex layers cover: relationship names (capitalized name following a relationship word), named facility types, specific court names and case numbers, medication names and diagnosis language, immigration and legal-status phrases, and date-plus-employment-event combinations at the sentence level. Findings span seven categories and deduplicate with more specific categories taking priority over broader ones. The Presidio engine is loaded at app boot via pii.warmup() called from create_app() to avoid a cold-start delay on the first scan.

## Content Configuration

Six content goals and seven audience profiles are defined as Python dictionaries in config/goals.py and config/audiences.py. Each goal carries a label, tone, target word length, and writing priority. Each audience carries a label, reading level, values statement, and extended writing guidance. These fields are injected into both the Ollama system prompt and the Claude user prompt at runtime. Carlos can update goal and audience configurations without touching application code.

## Security

The application implements several security controls:

- CSRF protection on all state-changing requests via Flask-WTF (CSRFProtect).

- Rate limiting on the login POST endpoint: 5 requests per minute and 20 per hour, enforced by Flask-Limiter keyed on remote IP address.

- Timing-safe password comparison using hmac.compare_digest to prevent timing attacks on the login route.

- Server-side filesystem sessions via Flask-Session so large conversation histories never overflow the cookie size limit.

- Message length cap of 2,000 characters enforced server-side on every /chat request.

## Known Limitation

When a staff member provides very short answers during the interview (under approximately 20 words per story element), Claude's no-fabrication constraint means the generated narrative will reflect that sparseness. The tool is working as designed — Claude was explicitly instructed never to invent details — but sparse input produces sparse output. Staff should be coached to provide enough detail during the interview for the narrative to be substantive.

## Testing

The Step 4 generator and the Step 5/6 PII pipeline were validated across five end-to-end test runs. Three tests used clean story starters with no PII expected; two deliberately planted violations to verify the scanner's detection logic. The results confirmed that the core architecture performs as designed across all five cases.

Test 1 used a workforce development story starter: "A young man in our program just started his first full-time job" with goal set to Report Impact to a Funder and audience set to Funders / Grant Officers. This was the first test of a male subject and a workforce development program type, neither of which had been heavily exercised during Weeks 2 and 3. The generator produced an evidence-first narrative appropriate to the funder audience, and the scanner returned clean with no flags.

Test 2 used a senior services story starter: "We helped an elderly client stay in her home” with goal set to Tell a Program Story and audience set to Community Members Served. This was the first test of an elderly subject. The generator handled age-related language appropriately and produced a plain-language, story-first output consistent with the 6–8th grade reading level target for that audience. The scanner returned clean.

Test 3 used a youth education story starter: “A teenager in our after-school program is doing better in school" — with goal set to Appeal to an Individual Donor and audience set to Individual Donors. This was the first test of a youth education population and also the first standalone test of the donor appeal goal, which had previously been combined with volunteer recruitment in a single goal slot. The generator produced an emotion-led output and closed with a direct giving ask. The scanner returned clean.

Test 4 was a deliberate PII test. The story starter: "Maria completed her treatment at Riverside Recovery Center and is doing well” planted two violations: a standalone first name and a specific facility name. Goal was set to Promote a Program or Service with audience set to Potential New Clients. The scanner correctly flagged "Maria" as a Category 1 direct identifier. "Riverside Recovery Center" was not flagged, however — not because the scanner failed, but because the Step 4 generator abstracted the facility name to "a dedicated facility" before the text ever reached the scanner. This is correct behavior for a public-facing narrative tool, and it is actually a meaningful data protection finding: the generation model is naturally inclined to de-identify when writing public copy. The practical implication for future regression testing is that facility-name detection in the Category 2 scanner cannot be tested through raw interview input alone — specific facility names must be injected directly into the Step 4 output to verify the regex fires.

Test 5 was the second deliberate PII test and the highest-priority case. The story starter: "We helped a client named Rosa and her daughter Sofia get stable after a really hard year"  plants the most common real-world PII mistake nonprofit staff make: naming both the client and a family member, particularly a child. Goal was set to Tell a Program Story with audience set to Partners / Peer Organizations. The scanner correctly flagged "Rosa" as a Category 1 direct identifier and "Sofia" as a Category 3 relationship identifier — a proper name immediately following the relationship keyword "daughter." Sofia was also flagged as a Category 2 location entity, a false positive attributable to the name matching a known geographic entity in the NER model. This is consistent with the scanner's design philosophy of erring toward over-flagging: a staff member can dismiss a false positive location flag in seconds, while a missed disclosure causes real harm.

Goal and audience alignment held across all five cases. Flesch readability scores tracked closely to target audience levels — a complex systemic narrative written for partner organizations scored at an 11th-grade reading level, while a crisis-intervention narrative written for potential new clients scored at a 6th-grade level. The deduplication logic in the findings list worked as intended, grouping multiple instances of the same flag into a single card with an occurrence count, keeping the review UI readable even in cases with high total occurrence counts.

The friction-based output model — warning banners, highlighted text, and actionable suggested fixes rather than hard blocks — proved appropriate for nonprofit staff use. The tool surfaces PII concerns as an educational checkpoint rather than an obstacle, which is the correct tradeoff for this user base.

# 8. Issues Faced

The most time-consuming problem was local model selection. Four models were evaluated and rejected before llama3.1:8b was selected. Mistral Nemo leaked system prompt text and output JSON before all five questions were answered. Gemma 2 9B was eliminated because it would comply with jailbreak-style inputs rather than hold its interviewer role. Qwen2.5 was fabricating story content, traced to a known chat template issue requiring the system field to be passed inside the messages array rather than as a top-level parameter. Llama 3.2 3B had the most natural conversational flow but leaked system prompt labels into responses and would eventually advance past unanswered questions after enough non-answer turns. Llama 3.1 8B resolved all of these failure modes and was the final selection.

Temperature tuning had a significant impact on reliability. At default temperatures, output varied noticeably between identical test runs, making it difficult to distinguish genuine failures from sampling artifacts. Lowering Ollama to 0.2 and Claude to 0.3 produced consistent, predictable output without losing the conversational quality the interview required.

Prompt engineering required several targeted fixes. A probe trigger was added to Q2 specifying that a time period or setting alone is insufficient. The model occasionally looped back to Q1 mid-interview, resolved by making the advancement rules more explicit. Raw quote extraction was the most persistent problem, requiring explicit prohibitions on paraphrasing and invention, along with specific criteria for what qualified as a valid quote.

Prompt-only enforcement proved insufficient for adversarial inputs. One-word responses and injection phrases would eventually cause model drift regardless of how the system prompt was written. The fix was intercepting those inputs in routes.py before they reached the model. Prompt-only enforcement has a hard ceiling, and application-layer controls are the correct place to handle reliability guarantees the model cannot enforce on its own.

Two PII scanner edge cases required fixes. Short all-caps tokens were being misclassified as location entities by the Presidio NER model and were reclassified as potential initials. Common capitalized words at sentence boundaries were triggering the relationship-name regex and were resolved with a pronoun and conjunction blacklist. The Presidio engine cold-start cost was addressed by calling warmup() from create_app() at boot.

# 9. Stakeholder Information

| Name | Carlos Morales |
| --- | --- |
| Company | Viva Technology LLC |
| Email | cmorales@vivatechnology.net |
| Phone | 612-325-3475 |

# 10. Reflection / Conclusion

When this project started, the part I expected to be hardest was the user interface. What actually proved most difficult was prompt engineering. Getting both the local model and Claude to behave reliably and consistently across all test cases took far more iteration than anticipated, and the solution ended up spanning both the system prompts and the application layer itself.

Model selection was more involved than I expected going in. I went through a significant number of local models before landing on the right one, and each failure taught me something specific about what these models can and cannot be trusted to do on their own.

The most significant conceptual shift was understanding that language models are probabilistic, not deterministic. Traditional software produces the same output given the same input every time. Language models do not, and that changes how you test, how you validate, and how you design for reliability. That insight shaped a lot of the architectural decisions you will see documented in Section 8.

The most unexpected learning came from outside the project itself. Using a Claude connector to generate my weekly progress reports directly from my ClickUp workspace introduced me to MCP, Model Context Protocol, and the broader pattern of connecting AI systems to external tools and data sources. That is something I will carry forward well beyond this course.

Looking at the finished application, what I am most proud of is that it is complete. Every step flows into the next without manual intervention, the output was validated against all six stakeholder story starters, and the security and reliability controls were built to a production standard rather than a prototype standard. If I were starting over, I would spend more time upfront researching which local models are suited for structured instruction-following tasks before committing to one. The testing process produced real knowledge, but better upfront research would have recovered the time it cost.

Thomas Brett  |  Lake Superior College  |  CIS 2987  |  April 26, 2026