CIS 2987 — Capstone Project Weekly Update

AI-Powered Storytelling Tool for Nonprofits

| Student: Thomas Brett | Week: 3 — Refining The Interview System |
| --- | --- |
| Course: CIS 2987 — CIS Capstone | Report Date: April 12, 2026 |
| PM Tool: ClickUp | Due Date: April 5, 2026 |

# 1. Detailed Task Breakdown (30-Minute Increments)

All tasks below are from the ClickUp list "Week 3 - Refining The Interview System" in the CIS Capstone space. Time estimates reflect actual development effort based on task complexity and scope.

| # | Task | Status | Est. Time | Actual Time | Variance |
| --- | --- | --- | --- | --- | --- |
| 1 | Test the extraction loop against all 6 story starters Carlos provided | Complete | 4:00 | 4:30 | +0:30 over |
| 2 | Fix edge cases — vague answers, very short answers, off-topic responses | Complete | 3:00 | 3:30 | +0:30 over |
| 3 | Confirm JSON output is consistently structured across all test runs | Complete | 2:30 | 2:30 | On target |
| 4 | Log the extraction completion rate across test stories | Complete | 1:30 | 1:30 | On target |
|  | Week 3 Total |  | 11:00 | 12:00 |  |

# 2. Weekly Reflections

What went well: The model evaluation process was structured and productive. Testing four models back-to-back with consistent test stories made it straightforward to identify failure modes and make a defensible final selection. Llama 3.1 8B proved to be the clear winner. The additional parameters compared to the 3B model made a meaningful difference in two key areas: context retention across longer conversations, and resistance to jailbreak-style inputs that caused other models to break character. Lowering the model temperature to 0.2 was also a significant factor in getting reliable, consistent output. At higher temperatures the model would occasionally drift in phrasing or deviate from the expected JSON structure. Bringing it down to 0.2 made responses much more deterministic and kept the extraction output predictable across runs. Two clean, validated end-to-end extraction runs with all five JSON fields correctly populated was the highlight of the week. Hardware held up well throughout, with the RTX 3080 handling all inference without any thermal or memory concerns. Challenges encountered: Getting models to reliably follow the system prompt was the central challenge. Gemma 2 9B was eliminated due to jailbreak compliance. When test inputs were designed to push the model out of its role, it would comply rather than hold its position. Qwen2.5 had a more subtle but critical failure: it was fabricating content and silently ignoring the system prompt entirely. This turned out to be a known chat template issue where the system field must be passed inside the messages array rather than at the top-level system parameter. Llama 3.2 3B had the most natural interview flow of any model tested but leaked prompt labels into responses and would eventually advance past unanswered questions after roughly 10 non-answer turns. Even with Llama 3.1 8B selected and temperature dialed down, one-word and non-answer inputs were still causing model drift over time. The fix was to intercept those at the Flask layer before they reached the model. Prompt-only enforcement has a hard ceiling, and application-level guardrails are the right architectural response. Noteworthy items: While jailbreak attempts are not a realistic threat in a controlled nonprofit tool, building that robustness in from the start is good engineering practice and worth documenting in the final report. The temperature adjustment to 0.2 is worth calling out specifically as a configuration decision with real impact on output quality. The app was also configured with ngrok to expose it outside the local network, with basic auth password protection added for remote stakeholder access. Overprobing was identified and documented as an intentional design tradeoff, favoring reliability of extraction over interview length, which is the right call for this use case.

# 3. Updated Project Timeline

The table below shows the planned vs. actual schedule for Week 3 tasks. All Week 3 tasks were completed within the reporting period.

| Task | Planned Due | Actual Completion | Status |
| --- | --- | --- | --- |
| Test extraction loop against all 6 story starters | 04/07/2026 | 04/08/2026 | ✓ Complete |
| Fix edge cases (vague, short, off-topic) | 04/08/2026 | 04/09/2026 | ✓ Complete |
| Confirm JSON output consistently structured | 04/09/2026 | 04/09/2026 | ✓ Complete |
| Log extraction completion rate | 04/10/2026 | 04/10/2026 | ✓ Complete |

Timeline Revision Notes: Week 3 work extended approximately one week beyond the original schedule due to the depth of model evaluation and refinement required. The interview pipeline is now functional and validated. A minor follow-on item has been identified: the system prompt needs a small adjustment to improve raw quote capture reliability, though overall extraction quality is strong. No specific blockers are causing the delay and the remaining phases are straightforward enough to recover the time. Weeks 4 through 6 are expected to proceed at an accelerated pace to bring the project back on schedule. Next week focuses on Claude API integration for narrative generation from the extracted JSON.

# 4. Proof of Completed Tasks

The following screenshots document task completion and are also stored as attachments on the corresponding ClickUp tasks.

Task 1: Test the extraction loop against story starters provided

Task 2: Fix edge cases — vague answers, very short answers, off-topic responses

Task 3: Confirm JSON output is consistently structured across all test runs

Task 4: Log the extraction completion rate across test stories

No applicable screenshot, 100% success rate on proper story element extraction.

# 5. Time Summary

| Category | Hours This Week | Cumulative Hours |
| --- | --- | --- |
| Development Tasks | 11:30 | 23:45 |
| Project Management / Reporting | 0:30 | 1:30 |
| Week 3 Total | 12:00 | 25:15 |

Project management/reporting time (0:30) includes updating ClickUp tasks, logging time, and preparing this weekly report, per capstone requirements.

Generated from ClickUp project management data — CIS Capstone Space, Week 3 - Refining The Interview System list. Thomas Brett, April 12, 2026.